## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 01. Information Search | 1.01 | Content variability | Search for a proper API | 2021-02-19 | 2021-03-05 | 100% | Radiy Matveev
2 | 01. Information Search | 1.01 | Content variability | Implement API | 2021-02-19 | 2021-03-05 | 100% | Suraj Kolari
3 | 01. Information Search | 1.01 | Content variability | Implement core functionality | 2021-02-19 | 2021-03-05 | 100% | Michael Lee
4 | 01. Information Search | 1.01 | Content variability | Implement GUI requirments | 2021-02-19 | 2021-03-05 | 100% | Rodrigo Martins
5 | 01. Information Search | 1.01 | Content variability | Develop Test Cases for Content variability | 2021-02-19 | 2021-03-05 | 100% | Swapnil Lonkar
6 | 01. Information Search | 1.01 | Content variability | Test Content variability functionality | 2021-02-19 | 2021-03-05 | 100% | Rodrigo Martins
7 | 01. Information Search | 1.01 | Content variability | Crosscut: Entitlements | 2021-02-19 | 2021-03-05 | 100% | Radiy Matveev
8 | 01. Information Search | 1.01 | Content variability | Crosscut: Connectivity | 2021-02-19 | 2021-03-05 | 100% | Suraj Kolari
9 | 01. Information Search | 1.01 | Content variability | Crosscut: In System Interface (inbound) | 2021-02-19 | 2021-03-05 | 100% | Michael Lee
10 | 04. User's Account | 4.03 | Modify General User's Information | Create Edit/Save Button | 2021-02-19 | 2021-03-01 | 100% | Rodrigo Martins
11 | 04. User's Account | 4.03 | Modify General User's Information | Implement core functionality | 2021-02-19 | 2021-03-01 | 100% | Swapnil Lonkar
12 | 04. User's Account | 4.03 | Modify General User's Information | Implement GUI requirments | 2021-02-19 | 2021-03-01 | 100% | Rodrigo Martins
13 | 04. User's Account | 4.03 | Modify General User's Information | Test Edit/Save button functionality | 2021-02-19 | 2021-03-01 | 100% | Rodrigo Martins
14 | 04. User's Account | 4.03 | Modify General User's Information | Crosscut: Exception Handling | 2021-02-19 | 2021-03-05 | 100% | Swapnil Lonkar
15 | 04. User's Account | 4.03 | Modify General User's Information | Crosscut: Security | 2021-02-19 | 2021-03-05 | 100% | Rodrigo Martins
16 | 04. User's Account | 4.03 | Modify General User's Information | Crosscut: Entitlements | 2021-02-19 | 2021-03-05 | 100% | Radiy Matveev

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 02. Sales Management | 2.02 | Ticket Sales | Search for a list of movie ticket sales paltforms | 2021-03-19 | 2021-03-25 | 0% | Swapnil Lonkar
2 | 02. Sales Management | 2.02 | Ticket Sales | Create a redirect button | 2021-03-19 | 2021-03-25 | 0% | Suraj Kolari
3 | 02. Sales Management | 2.02 | Ticket Sales | Implement core functionality | 2021-03-19 | 2021-03-25 | 0% | Rodrigo Martins
4 | 02. Sales Management | 2.02 | Ticket Sales | Implement GUI requirments | 2021-03-19 | 2021-03-25 | 0% | Swapnil Lonkar
5 | 02. Sales Management | 2.02 | Ticket Sales | Develop test Cases for Ticket Sales functionality | 2021-03-19 | 2021-03-25 | 0% | Radiy Matveev
6 | 02. Sales Management | 2.02 | Ticket Sales | Test Tickets Sales functionality | 2021-03-19 | 2021-03-25 | 0% | Suraj Kolari
7 | 02. Sales Management | 2.02 | Ticket Sales | Crosscut: Out - System Interface (outbound) | 2021-03-19 | 2021-03-25 | 0% | Swapnil Lonkar
8 | 02. Sales Management | 2.02 | Ticket Sales | Crosscut: Entitlements | 2021-03-19 | 2021-03-25 | 0% | Suraj Kolari
9 | 04. User's Account | 4.04 | Contact Customer Support | Create a submission form | 2021-03-19 | 2021-03-26 | 0% | Suraj Kolari
10 | 04. User's Account | 4.04 | Contact Customer Support | Implement core functionality | 2021-03-19 | 2021-03-26 | 0% | Michael Lee
11 | 04. User's Account | 4.04 | Contact Customer Support | Implement GUI requirments | 2021-03-19 | 2021-03-26 | 0% | Radiy Matveev
12 | 04. User's Account | 4.04 | Contact Customer Support | Develop Test Cases for User Relationship functionality | 2021-03-19 | 2021-03-26 | 0% | Rucha Madan
13 | 04. User's Account | 4.04 | Contact Customer Support | Test User Relationship functionality | 2021-03-19 | 2021-03-26 | 0% | Rucha Madan
14 | 04. User's Account | 4.04 | Contact Customer Support | Crosscut: In - Data Flow In | 2021-03-19 | 2021-03-26 | 0% | Suraj Kolari
15 | 04. User's Account | 4.04 | Contact Customer Support | Crosscut: Data Flow Out | 2021-03-19 | 2021-03-26 | 0% | Michael Lee
16 | 04. User's Account | 4.04 | Contact Customer Support | Crosscut: Entitlements | 2021-03-19 | 2021-03-26 | 0% | Radiy Matveev

## I3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 03. User Experience | 3.02 | User Relationship | Create a submission form | 2021-04-02 | 2021-04-09 | 0% | Michael Lee
2 | 03. User Experience | 3.02 | User Relationship | Implement core functionality | 2021-04-02 | 2021-04-09 | 0% | Michael Lee
2 | 03. User Experience | 3.02 | User Relationship | Implement GUI requirments | 2021-04-02 | 2021-04-09 | 0% | Radiy Matveev
3 | 03. User Experience | 3.02 | User Relationship | Develop Test Cases for User Relationship functionality | 2021-04-02 | 2021-04-09 | 0% | Suraj Kolari
3 | 03. User Experience | 3.02 | User Relationship | Test User Relationship functionality | 2021-04-02 | 2021-04-09 | 0% | Michael Lee
4 | 03. User Experience | 3.02 | User Relationship | Crosscut: Field Validation | 2021-04-02 | 2021-04-09 | 0% | Michael Lee
4 | 03. User Experience | 3.02 | User Relationship | Crosscut: Concurrency | 2021-04-02 | 2021-04-09 | 0% | Michael Lee
5 | 03. User Experience | 3.02 | User Relationship | Crosscut: Entitlements | 2021-04-02 | 2021-04-09 | 0% | Radiy Matveev

## I4
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 02. Sales Management | 2.01 | Ads | Search for a proper API | 2021-04-16 | 2021-04-30 | 0% | Rodrigo Martins
2 | 02. Sales Management | 2.01 | Ads | Implement API | 2021-04-16 | 2021-04-30 | 0% | Suraj Kolari
3 | 02. Sales Management | 2.01 | Ads | Implement core functionality | 2021-04-16 | 2021-04-30 | 0% | Michael Lee
4 | 02. Sales Management | 2.01 | Ads | Implement GUI requirments | 2021-04-16 | 2021-04-30 | 0% | Radiy Matveev
5 | 02. Sales Management | 2.01 | Ads | Develop Test Cases for Google Ads | 2021-04-16 | 2021-04-30 | 0% | Rucha Madan
6 | 02. Sales Management | 2.01 | Ads | Test Google Ads visibility | 2021-04-16 | 2021-04-30 | 0% | Rucha Madan
7 | 02. Sales Management | 2.01 | Ads | Crosscut: In System Interface (inbound) | 2021-04-16 | 2021-04-30 | 0% | Rodrigo Martins
8 | 02. Sales Management | 2.01 | Ads | Crosscut: Out - Data Flow Out (outbound) | 2021-04-16 | 2021-04-30 | 0% | Suraj Kolari
9 | 04. User's Account | 4.05 | Delete an Account | Create Delete button | 2021-04-16 | 2021-04-27 | 0% | Swapnil Lonkar
10 | 04. User's Account | 4.05 | Delete an Account | Implement core functionality | 2021-04-16 | 2021-04-27 | 0% | Swapnil Lonkar
11 | 04. User's Account | 4.05 | Delete an Account | Implement GUI requirments | 2021-04-16 | 2021-04-27 | 0% | Swapnil Lonkar
12 | 04. User's Account | 4.05 | Delete an Account | Test Delete button | 2021-04-16 | 2021-04-27 | 0% | Swapnil Lonkar
13 | 04. User's Account | 4.05 | Delete an Account | Crosscut: Security | 2021-04-16 | 2021-04-27 | 0% | Swapnil Lonkar
14 | 04. User's Account | 4.05 | Delete an Account | Crosscut: Exception Handling | 2021-04-16 | 2021-04-27 | 0% | Swapnil Lonkar