## Initial Plan
Color Coding |  |  | Completed |  |  |  | FALL 2020 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
[6 empty] | Date | 2020-09-01 | 2020-09-08 | 2020-09-15 | 2020-09-22 | 2020-09-29 | 2020-10-06 | 2020-10-13 | 2020-10-20 | 2020-10-27 | 2020-11-03 | 2020-11-10 | 2020-11-17 | 2018-11-24
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2020-08-27 | 2020-08-28 | 100%
| Confirm Project Team Roles |  | ALL | 2020-08-25 | 2020-08-25 | 100%
| Develop two business cases |  | Swapnil Lonkar | 2020-08-27 | 2020-08-28 | 100%
| Develop Project Initiation Document (PID) |  | Rucha Madan | 2020-09-03 | 2020-09-22 | 100%
| Produce initial Project Plan, RACI |  | Rucha Madan | 2020-09-10 | 2020-09-22 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Swapnil Lonkar | 2020-09-17 | 2020-09-22 | 100%
| Produce Context Diagram, Define System Interfaces |  | Swapnil Lonkar | 2020-09-17 | 2020-09-22 | 100%
| Define Business Requirements |  | Michael Lee | 2020-09-17 | 2020-09-28 | 100%
| Agree to System Requirements types |  | All | 2020-09-17 | 2020-09-28 | 100%
| Define Functional Decomposition |  | All | 2020-09-24 | 2020-09-28 | 100%
| Produce RCT document |  | Swapnil Lonkar | 2020-09-24 | 2020-09-28 | 100%
| Decide which features to implement this semester |  | All | 2020-09-30 | 2020-10-13 | 100%
| Produce analysis diagrams (UML, DFD) |  | Swapnil Lonkar | 2020-09-30 | 2020-10-20 | 100%
| Define functional requirements (User Stories) |  | Swapnil Lonkar | 2020-09-30 | 2020-10-05 | 100%
| Update Project Plan with additional requirements tasks |  | Rucha Madan | 2020-09-30 | 2020-10-13 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) |  | Radiy Matveev | 2020-10-22 | 2020-10-23 | 100%
| Database Design (ERD, Table spec) |  | Rodrigo Martins | 2020-10-15 | 2020-10-20 | 100%
| System Interface Design |  | Radiy Matveev | 2020-10-22 | 2020-10-27 | 100%
| User interface design |  | Radiy Matveev | 2020-10-22 | 2020-10-27 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | 01.01 Content variability | GUI & Functionality Detailed Design | Radiy Matveev | 2020-10-22 | 2020-11-03 | 100%
| 05.01 Create an Account | Coding & Implemenation | Radiy Matveev | 2020-10-27 | 2020-11-03 | 100%
| 05.02 Sign into Account | Coding & Implemenation | Radiy Matveev | 2020-10-27 | 2020-11-03 | 100%
| 05.03 Modify General User's Information | Coding & Implemenation | Radiy Matveev | 2020-10-27 | 2020-11-03 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  | Suraj Kolari | 2020-11-05 | 2020-11-10 | 50%
| Evaluate Features to be Tested |  | Suraj Kolari | 2020-11-05 | 2020-11-10 | 50%
| Design Test Cases |  | Suraj Kolari | 2020-11-05 | 2020-11-10 | 50%
| Execute Test Cases |  | Suraj Kolari | 2020-11-05 | 2020-11-10 | 50%
| Anaylze Test Results |  | ALL | 2020-11-10 | TBD | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2020-11-24 | TBD | 0%

## Final Plan
Color Coding |  |  | Completed |  |  |  | SPRING 2018 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2018-01-30 | 2018-02-06 | 2017-02-13 | 2018-02-20 | 2018-02-27 | 2018-03-06 | 2018-03-13 | 2018-03-20 | 2018-03-27 | 2018-04-03 | 2018-04-10 | 2018-04-17 | 2018-04-24 | 2018-05-01 | 2018-05-08
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2018-01-23 | 2018-01-27 | 100%
| Confirm Project Team Roles |  | ALL | 2018-01-23 | 2018-01-27 | 100%
| Develop two business cases |  | Mohd Shaarif Khan | 2018-02-03 | 2018-02-07 | 100%
| Develop Project Initiation Document (PID) |  | Nahush Pawar | 2018-02-08 | 2018-02-10 | 100%
| Produce initial Project Plan, RACI |  | Mohd Shaarif Khan | 2018-02-13 | 2018-02-20 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Nahush Pawar | 2018-01-28 | 2017-02-05 | 100%
| Produce Context Diagram, Define System Interfaces |  | Vikalp Shastri | 2018-02-20 | 2018-02-27 | 100%
| Define Business Requirements |  | Vikalp Shastri | 2018-02-13 | 2018-03-06 | 100%
| Agree to System Requirements types |  | All | 2018-02-27 | 2018-03-06 | 100%
| Define Functional Decomposition |  | All | 2018-02-27 | 2018-03-06 | 100%
| Produce RCT document |  | Vikalp Shastri | 2018-02-27 | 2018-03-06 | 100%
| Decide which features to implement this semester |  | All | 2018-03-06 | 2018-03-13 | 100%
| Produce analysis diagrams (UML, DFD) |  | Vikalp Shastri | 2018-03-06 | 2018-03-13 | 100%
| Define functional requirements (User Stories) |  | Vikalp Shastri | 2018-03-06 | 2018-03-13 | 100%
| Update Project Plan with additional requirements tasks |  | Mohd Shaarif Khan | 2018-02-27 | 2018-03-06 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) |  | Rohan Kulkarni | 2018-03-27 | 2017-04-03 | 100%
| Database Design (ERD, Table spec) |  | Divya Kodi | 2018-03-20 | 2018-03-27 | 100%
| System Interface Design |  | Rohan Kulkarni | 2018-03-27 | 2018-04-03 | 100%
| User interface design |  | Rohan Kulkarni | 2018-04-03 | 2018-04-10 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | User Portal | GUI & Functionality Design | Rohan Kulkarni Divya Kodi | 2018-03-06 | 2018-03-20 | 100%
|  | Coding | Rohan Kulkarni | 2018-03-06 | 2018-03-20 | 100%
| Admin Portal | GUI & Functionality Design | Rohan Kulkarni Divya Kodi | 2018-03-20 | 2018-03-27 | 100%
|  | Coding | Rohan Kulkarni | 2018-03-20 | 2018-03-27 | 100%
| Search Car | GUI & Functionality Design | Rohan Kulkarni Divya Kodi | 2018-03-27 | 2018-04-03 | 100%
|  | Coding | Rohan Kulkarni | 2018-03-27 | 2018-04-03 | 100%
| View car Availability | GUI & Functionality Design | Rohan Kulkarni Divya Kodi | 2018-04-03 | 2018-04-10 | 100%
|  | Coding | Rohan Kulkarni | 2018-04-03 | 2018-04-10 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  | Rahul Vasaikar | 2018-03-27 | 2018-04-24 | 0%
| Evaluate Features to be Tested |  | ALL | 2018-03-27 | 2018-04-24 | 100%
| User Portal | Design Test Cases | Rahul Vasaikar | 2018-03-27 | 2018-04-03 | 100%
|  | Execute Test Cases | Rahul Vasaikar Charitha Suresh | 2018-04-03 | 2018-04-10 | 100%
|  | Anaylze Test Results | ALL | 2018-04-10 | 2018-04-17 | 100%
| Admin Portal | Design Test Cases | Rahul Vasaikar | 2018-03-27 | 2018-04-03 | 100%
|  | Execute Test Cases | Rahul Vasaikar Charitha Suresh | 2018-04-03 | 2018-04-10 | 100%
|  | Anaylze Test Results | ALL | 2018-04-10 | 2018-04-17 | 100%
| Search Car | Design Test Cases | Rahul Vasaikar | 2018-03-27 | 2018-04-03 | 100%
|  | Execute Test Cases | Rahul Vasaikar Charitha Suresh | 2018-04-03 | 2018-04-10 | 100%
|  | Anaylze Test Results | ALL | 2018-04-10 | 2018-04-17 | 100%
| View car Availability | Design Test Cases | Rahul Vasaikar | 2018-03-27 | 2018-04-03 | 100%
|  | Execute Test Cases | Rahul Vasaikar Charitha Suresh | 2018-04-03 | 2018-04-10 | 100%
|  | Anaylze Test Results | ALL | 2018-04-10 | 2018-04-17 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2018-05-01 | 2018-05-08 | 100%