## Road Map
Bulletin
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 2/26/21 | Iteration 2 - 03/26/21 | Iteration 3 - 04/09/21 | Iteration 4 - 04/23/21
Module 1 - Information Search | 01.01 Content variability | 5 | x
Module 2 - Sales Management | 02.01 Ad Content | 5 |  |  |  | x
| 02.02 Ticket Sales | 3 |  | x
Module 3 - User Experience | 03.01 Maintenance | 4
| 03.02 User Relationship | 4 |  |  | x
Module 4 - User's Account | 04.01 Create an Account | 4
| 04.02 Sign into Account | 2
| 04.03 Modify General User's Information | 3 | x
| 04.04 Contact Customer Support | 3 |  | x
| 04.05 Delete an Account | 3 |  |  |  | x
|  | Velocity : | 8 | 6 | 4 | 8
In GREEN features implemented last semester

## Story Map
Epics |  | Movie Library Database (MLDB) - User Story Map
Epic 1 - Information Search |  | Epic 1 - Information Search | Epic 2 - Sales Management | Epic 3 - User Experience | Epic 4 - User's Account
Epic 2 - Sales Management | User Stories | 01.01 Content variability |  |  | 04.03 Modify General User's Information | Iteration 1
Epic 3 - User Experience
Epic 4 - User's Account |  |  | 02.02 Ticket Sales |  | 04.04 Contact Customer Support | Iteration 2
|  |  |  | 03.02 User Relationship |  | Iteration 3
|  |  | 02.01 Ad Content |  | 04.05 Delete an Account | Iteration 4