## Functional Decomposition
Functional Decomposition
Module Name | Brief Description
01. Information Search | Information Search' module gives the ability to manage the content. The module is compound of the following functionality: Ability to create/edit content within the web application, ability to streamline partner’s content on our web application.
02. Sales Management | Sales Management' module is compound of the following functionality: Ad Contents and Ticket Sales.
03. User Experience | User Experience' module is compound of Maintaince and user relationship which incorporates ability to maintain stability of the web application, ability to edit web application functionality, ability to provide customer support.
04. User's Account | User's Account module is compound of the following functionality: create an account, sign into account, delete an account, modify user's general information, see movie ratings and contact customer support.

## RTM
Requirements Traceability Matrix. MLDB Web Application
|  | 01. Information Search | 02. Sales Management |  | 03. User Experience |  | 04. User's Account
|  | 01.01 Content variability | 02.01 Ad Content | 02.02 Ticket Sales | 03.01 Maintenance | 03.02 User Relationship | 04.01 Create an Account | 04.02 Sign into Account | 04.03 Modify General User's Information | 04.04 Contact a Customer Support | 04.05 Delete an Account
4.2.1 Content Management | 4.2.1.1 Ability to create/edit content within the web application | X
| 4.2.1.2 Ability to block users |  |  |  |  | X
| 4.2.1.3 Ability to streamline partner’s content on our web application | X
4.2.2 Advertisement Management | 4.2.3.1 Ability to generate sponsored ads and listings |  | X
4.2.3.2 Ability to request statistical information
| 4.2.3.2 Ability to keep ads up-to-date |  | X
4.2.3 Customer Requirements | 4.2.5.1 Ability to open up web page | X |  | X
| 4.2.5.2 Ability to create and log in to personal account and have complete control of the account | [5 empty] | X | X |  |  | X
| 4.2.5.4 Ability to sign-in to pre-existing account | [7 empty] | X
4.2.4 Operations Management | 4.2.6.1 Ability to maintain stability of the web application |  | X |  | X
| 4.2.6.2 Ability to edit web application functionality |  |  |  | X
| 4.2.6.2 Ability to provide customer support |  |  |  |  | X |  |  |  | X

## Crosscut Description
Crosscutting Concerns | Descriptions | Test Ideas
ET - Entitlements | This concern relates to different internal user access privileges (roles) and how they impact the behavior of core features. List of User Roles: members and guests | TBD
FV - Field Validation | This concern relates to validating individual data entry fields | User needs to use to his/her email address to make profile and for the first time email verification is required.
DDV - Data-Dependency Validation | This concern relates to validating field value combinations. It also includes validation of constrains, for example, a currency cannot be make inactive if it has outstanding orders/trades | TBD
DDD - Data-Driven Defaults | This concern relates to populating field default values based on another field value | TBD
CL - Calculations | This concern represents various "behind-the-screen" calculations that are executed in the context of core features | TBD
ER - Enrichment | This concern relates to any data enrichment being applied on top of clients data | TBD
CC - Concurrency | This concern relates to simultaneous data manipulation by more than one user. For example, both users see the same order. User 1 tries to modify this order, whereas User 2 tries to execute this order | TBD
CN - Connectivity | This concern relates to the architecture of an application where the front-end can be disconnected from the back end and that would change the behavior of some core features | TBD
DF-In - Data Flow In | This concern addresses the core feature behavior when it takes data in from another core feature of the same application | TBD
DF-Out - Data Flow Out | This concern addresses the core feature behavior when it generates data used by other core feature(s) of the same application | TBD
SE-Security
SI-In System Interface (inbound) | This concern relates to data coming from external applications and indicates which of the core features consume such data. Including this concern can help a team to better plan E2E testing and analyze the impact of changes from other applications | TBD
SI-Out - System Interface (outbound) | This concern relates to data passed to external applications and indicates which of the core features generate such data. Including this concern can help a team to better plan E2E testing and analyze the impact of changes on other applications | TBD
CA - Cache | Concerns non-core-feature data flow in. For example, static data cached in the component is a concern but is does not flow into the component as part of a trade booking. | TBD
ExH - Exception Handling | This concern relates to any exception handling (raising of exception) or rejection of trade/wire. | TBD
PF - Performance | This concern relates to performance requirements affecting some of the core features. | Tool needed : Load Runner

## RCT Details
Requirements Composition Table. MLDB Web Application
List of Concerns | 01. Information Search | 02. Sales Management |  | 03. User Experience |  | 04. User's Account
| 01.01 Content variability | 02.01 Ad Content | 02.02 Ticket Sales | 03.01 Maintenance | 03.02 User Relationship | 04.01 Create an Account | 04.02 Sign into Account | 04.03 Modify General User's Information | 04.04 Contact a Customer Support | 04.05 Delete an Account | Crosscut Counts
Core Functionality | I1 | I4 | I2 | 1 | I3 | 1 | 1 | I1 | I2 | I4
GUI Features | I1 | I4 | I2 | 1 | I3 | 1 | 1 | I1 | I2 | I4
Crosscutting Concerns
EN- Entitlements | I1 | 0 | I2 | 0 | I3 | 1 | 1 | I1 | I2 | I4 | 7
FV - Field Validation | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10
DDV - Data-Dependency Validation | I1 | I4 | I2 | 1 | I3 | 1 | 1 | I1 | I2 | I4 | 10
DDD - Data-Driven Defaults | I1 | I4 | I2 | 1 | I3 | 1 | 1 | I1 | I2 | I4 | 10
CL - Calculations | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4
ER - Enrichment | I1 | I4 | I2 | 1 | I3 | 0 | 0 | 0 | 0 | 0 | 4
CN - Connectivity | I1 | I4 | I2 | 1 | I3 | 1 | 1 | I1 | I2 | I4 | 10
DF-In - Data Flow In | I1 | I4 | I2 | 1 | I3 | 0 | 0 | 0 | 0 | 0 | 3
DF-Out - Data Flow Out | I1 | I4 | I2 | 1 | I3 | 1 | 1 | I1 | I2 | I4 | 10
SI-In System Interface (inbound) | I1 | I4 | I2 | 1 | I3 | 0 | 0 | 0 | 0 | 0 | 3
SI-Out - System Interface (outbound) | I1 | I4 | I2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
CC - Concurrency | I1 | I4 | 0 | 0 | 0 | 0 | 0 | I1 | 0 | 0 | 4
CA - Cache | I1 | I4 | I2 | 1 | I3 | 1 | 1 | I1 | I2 | I4 | 10
SE - Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I1 | I2 | I4 | 3
ExH - Exception Handling | I1 | I4 | I2 | 1 | I3 | 1 | 1 | I1 | I2 | I4 | 10
PF - Performance | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10
Features to implement this semester

## Feature Short Description
Module | Core Feature Name | Feature Short Descriptions
01. Information Search | 01.01 Content variability | This feature allows variety of movie posters to be displayed on the home page of the application. As well as it provides the ability to search and browse all the available movie poster throughout the application.
02. Sales Management | 02.01 Ad Contents | This feature allows ability to generate sponsored ads and listings and to keep ads up-to-date.
| 02.02 Ticket Sales | This feature allows web user to view and purchase movie tickets from tickets sales partner.
03. User Experience | 03.01 Maintenance | This feature allows to maintain stability of the web application and edit web application functionality
| 03.02 User Relationship | This feature allows a web user to receive customer support
04. User's Account | 04.01 Create an Account | This feature allows a web user to open an account.
| 04.02 Sign into Account | This feature allow a web user to sign into his accout.
| 04.03 Modify General user's Information | This feature allows web user to modify existing web user's information.
| 04.04 Contact a Customer Support | This feature allows a web user to email a customer support team.
| 04.05 Delete an Account | This feature allows a web user to delete an account.

## ET-Entitlements
Entitlements Specification. MLDB Web Application
User Roles | 01. Information Search | 02. Sales Management |  | 03. User Experience |  | 04. User's Account
| 01.01 Content variability | 02.01 Ad Content | 02.02 Ticket Sales | 03.01 Maintenance | 03.02 User Relationship | 04.01 Create an Account | 04.02 Sign into Account | 04.03 Modify General User's Information | 04.04 Contact a Customer Support | 04.05 Delete an Account
Relationship Management | x |  |  |  | x
Advertisement Sales Representative |  | x | x
Web User | x |  |  |  |  | x | x | x | x | x
Operation Management |  |  |  | x